## RAP - Plan A
SL | Resource Type | Week1 | Week2 | Week3 | Week4 | Total

## Details_break_down(WBS)
# | Task Module | Features To be implemented | Activities to be done | App Dev (man-Day | Start Date | End Date | Module Total (man-month)
Week 1
1 | Project Initiation
|  | 1.1 Define scope and objective | 1.1.1 Conduct a feasibility study | 2 | 2/2/23 | 3/3/23
|  |  | 1.1.2 Project scope, objective and constraints should be defined. | 3 | 2/2/23 | 3/2/23
|  |  | 1.1.3 Creating a high-level project plan and timeline | 3 | 2/2/23 | 3/2/23
2 | Requirement Understanding
|  | 2.1 Gather Requirements | 2.1.1 Collecting requirements from trainers | 1 | 3/2/23 | 4/2/23
|  |  | 2.1.2 Sharing assumptions and taking feedback. | 1 | 3/2/23 | 4/2/23
|  | 2.2 Preparing SRS | 2.2.1 Analyzing Requirements | 1 | 3/2/23 | 4/2/23
|  |  | 2.2.2 Validating Requirements | 0.5 | 3/2/23 | 4/2/23
|  |  | 2.2.3 Determining functional requirements | 1.5 | 3/2/23 | 4/2/23
|  |  | 2.2.4 Determining Non-functional requirements | 1.5 | 3/2/23 | 4/2/23
|  |  | 2.2.5 Prioritizing Requirements | 0.5 | 3/2/23 | 4/2/23
|  |  | 2.2.6 Ensure Requirement Traceability | 0.5 | 3/2/23 | 4/2/23
3 | Planning
|  | 3.1 Project Plan | 3.1.1 Develop a detailed project plan including resources, timeline and risks | 8 | 4/2/23 | 5/2/23
|  |  | 3.1.2 Develop risk management plan | 4 | 5/2/23 | 6/2/23
4 | Design Documents
|  | 4.1 Draw UML Diagrams | 4.1.1 Use Case Diagram | 2 | 6/2/23 | 7/2/23
|  |  | 4.1.2 Data Flow Diagram | 2 | 5/2/23 | 7/2/23
|  |  | 4.1.3 Activity Diagram | 2 | 6/2/23 | 7/2/23
|  |  | 4.1.4 ERD Diagram | 2 | 6/2/23 | 7/2/23
Week 2
5 | Data Analysis
|  | 5.1 Prepare API Documentation | 5.1.1 Analyse all available API endpoints | 16 | 8/2/23 | 10/2/23
|  |  | 5.1.2 Find endpoints that are needed as per required features | 8 | 10/2/23 | 11/2/23
|  |  | 5.1.3 Test the API calls | 4 | 11/2/23 | 11/2/23
|  |  | 5.1.4 Document the findings | 8 | 11/2/23 | 12/2/23
Week 3 & 4
6 | Design
|  | 6.1 Database Design | 6.1.1 Database schema designing | 2 | 13/2/23 | 13/2/23
|  |  | 6.1.2 Defining database entities and relationships | 4 | 13/2/23 | 13/2/23
|  | 6.2 Design User Interface | 6.2.1 Sketch mock UI | 4 | 14/2/23 | 14/2/23
|  |  | 6.1.2 Design and integrate UI elements | 12 | 14/2/23 | 15/2/23
|  | 6.3 Design Application Architecture | 6.3.1 Implement MVVM pattern | 2 | 16/2/23 | 17/2/23
|  |  | 6.3.2 Implement Adapter pattern | 1 | 16/2/23 | 17/2/23
|  | 6.4 Backend Development | 6.4.1 Integrate API with the app | 1 | 16/2/23 | 17/2/23
|  |  | 6.4.2 Connect to API endpoints to fetch data | 0.5 | 16/2/23 | 17/2/23
|  |  | 6.4.3 Store the fetched data into local database | 2.5 | 16/2/23 | 17/2/23
|  | 6.5 Frontend Development | 6.5.1 Establish frontend-backend connection | 2 | 18/2/23 | 19/2/23
|  |  | 6.5.2 Bind data from repository to ViewModel and update UI accordingly | 6 | 18/2/23 | 19/2/23
7 | Testing & Quality Assurance
|  | 7.1 Conduct app functionality testing | 7.1.1 Create test cases | 1 | 19/2/23 | 20/2/23
|  |  | 7.1.2 Test functional and non-functional features | 6 | 19/2/23 | 20/2/23
|  |  | 7.1.3 Testing on physical device | 1 | 19/2/23 | 20/2/23
|  | 7.2 Identiying and fixing bugs | 7.2.1 Debugging and resolving possible crashes | 16 | 21/2/23 | 23/2/23
8 | Final Submission
|  | 8.1 Cleaning Code | 8.1.1 Ensure clean coding conventions are followed throughout the project. Utilize App Inspection feature. | 8 | 23/2/23 | 23/2/23
|  | 8.2 Update documents | 8.2.1 Apply necessary fixes and changes to the documents. | 4 | 24/2/23 | 24/2/23
|  | 8.3 Prepare for Presentation | 8.3.1 Prepare slides & Rehearse | 12 | 24/2/23 | 25/2/23
#REF!