## RAP - Plan A
SL | Resource Type | Week1 | Week2 | Week3 | Week4 | Total

## Details_break_down(WBS)
# | Task Module | Features To be implemented | Activities to be done | App Dev (man-Day | Start Date | End Date | Module Total (man-month)
1 | Requirement Understanding | 1.1 Planning Preparation | 1.1.1 Understanding the Scope and Objective | 3 | 2023-02-02 | 2023-02-03
|  |  | 1.1.2 Develop Delivery Time | 3 | 2023-02-02 | 2023-02-03
|  | 1.2 Gathering Requirement | 1.2.1 Identify resources and requirements | 3 | 2023-02-02 | 2023-02-03
|  |  | 1.2.2 Understanding Functional Requirement | 4 | 2023-02-03 | 2023-02-04
|  |  | 1.2.3 Identifying Non Functional Requirement | 4 | 2023-02-03 | 2023-02-04
2 | Documentation and Diagram | 2.1 Documentation | 2.1.1 Write Software Requirement Specification | 8 | 2023-02-04 | 2023-02-05
|  |  | 2.1.3 Develop technical documentation Work Breakdown Structure | 8 | 2023-02-05 | 2023-02-05
|  | 2.2 Diagram | 2.2.1 Activity Diagram | 3 | 2023-02-06 | 2023-02-06
|  |  | 2.2.2 ERD Diagram | 3 | 2023-02-06 | 2023-02-06
|  |  | 2.2.3 Sequence Diagram | 3 | 2023-02-06 | 2023-02-06
|  | 3.1 Understanding API | 3.1.1 Understand requirement for API document feature | 16 | 2023-07-02 | 2023-08-02
|  | 3.2 Design Based on APi | 3.2.1 Create a Design Concept Based on API | 8 | 2023-09-02 | 2023-09-02
3 | API Analysis |  | 3.2.2 Identify Required elements | 3 | 2023-10-02 | 2023-10-02
|  | 3.3 API Documentation | 3.3.1 Create Draft based on Analysis | 3 | 2023-10-02 | 2023-10-02
|  |  | 3.3.2 Finalize Draft | 8 | 2023-10-02 | 2023-10-02
4 | Development | 4.1 UI Design | 4.1.1 Design UI Components | 8 | 2023-11-02 | 2023-11-02
|  | 4.2 Backend Development | 4.2.1 Connect to API for Cricket Data | 16 | 2023-12-02 | 13/2/2023
|  |  | 4.2.2 Implement Database | 16 | 14/2/2023 | 15/2/2023
|  |  | 4.2.3 Store Data from API | 16 | 16/2/2023 | 17/2/2023
|  | 4.3 Frontend Development | 4.3.1 Implement UI Components | 16 | 18/2/2023 | 19/2/2023
|  |  | 4.3.2 Connect Backend with Frontend | 16 | 20/2/2023 | 21/2/2023
5 | Quality Assurance | 5.1 Test app functionality | 5.1.1 Create test case | 4 | 22/2/2023 | 22/2/2023
|  |  | 5.1.2. Execute functional and non-functional testing | 4 | 22/2/2023 | 22/2/2023
|  |  | 5.1.3. Perform manual testing on device | 2 | 22/2/2023 | 22/2/2023
|  | 5.2 Identify and fix bug | 5.2.1. Identify Bugs | 4 | 23/2/2023 | 23/2/2023
|  |  | 5.2.2 Implement fix | 4 | 23/2/2023 | 23/2/2023
6 | Preparing Final Submission | 6.1 Cleaning | 6.1.1 Clean the Code | 1 | 24/2/2023 | 24/2/2023
|  |  | 6.1.2 Organize the code | 1 | 24/2/2023 | 24/2/2023
|  | 6.2 Fix Documents | 6.2.1 Organize all the documents | 2 | 24/2/2023 | 24/2/2023
|  |  | 6.2.2 Implement feedback | 3 | 24/2/2023 | 24/2/2023
|  | 6.3 Presentation Preparation | 6.3.1 Prepare Slide | 3 | 25/2/2023 | 25/2/2023
|  |  | 6.3.4 Prepare presenation and Practice | 2 | 25/2/2023 | 25/2/2023
#REF!