## Sheet1
Sl No | Task Module | Features to be Implemented | Activities to be done | Webapp Dev (man-day) | Start Date | End Date | Module Total (man-month)
Week 1
1 | Requirement Understanding | 1.1 Project Planning | 1.1.1 Understanding the Scope and Objective | 4 | 2023-07-03 | 2023-07-03
|  |  | 1.1.2 Develop Project Schedule | 2 | 2023-07-03 | 2023-07-03
|  |  | 1.1.3 Develop Delivery Plan | 2 | 2023-07-03 | 2023-07-03
|  | 1.2 Requirements Gathering | 1.2.1 Understanding product perspective, functions | 4 | 2023-07-04 | 2023-07-04
|  |  | 1.2.2 Identifying constraints, assumptions and dependencies | 2 | 2023-07-04 | 2023-07-05
|  |  | 1.2.3 Understanding Funtional Requirements | 8 | 2023-07-05 | 2023-07-05
|  |  | 1.2.4 Understanding Non-funtional Requirements | 4 | 2023-07-06 | 2023-07-06
2 | Documentation and Diagram | 2.1 Documentation | 2.1.1 Write Software Requirement Specification | 2 | 2023-07-06 | 2023-07-06
|  |  | 2.1.2 Develop Work Breakdown Structure | 2 | 2023-07-06 | 2023-07-06
|  | 2.2 Diagram | 2.2.1 Use Case Diagram | 2 | 2023-07-06 | 2023-07-06
|  |  | 2.2.2 Class Diagram | 4 | 2023-07-07 | 2023-07-07
|  |  | 2.2.3 Entity-Relationship Diagram (ERD) | 4 | 2023-07-07 | 2023-07-07
|  |  | 2.2.4 Activity Diagram | 2 | 2023-07-07 | 2023-07-07
Week 2
3 | API Analysis | 3.1 Understanding API | 3.1.1 Understand requirement for API documentation | 3 | 2023-07-08 | 2023-07-08
|  |  | 3.1.2 Analyze all available API endpoints | 3 | 2023-07-08 | 2023-07-08
|  |  | 3.1.3 Find required enpoints for features | 3 | 2023-07-08 | 2023-07-08
|  | 3.2 Designed Based on API | 3.2.1 Create a Design Concept Based on API | 3 | 2023-07-09 | 2023-07-09
|  |  | 3.2.2 Analyze all the APIs | 3 | 2023-07-09 | 2023-07-09
|  | 3.3 API Documentation | 3.3.1 Create draft based on analysis | 3 | 2023-07-09 | 2023-07-09
|  |  | 3.3.2 Finalize Draft | 3 | 2023-07-10 | 2023-07-10
4 | System Design | 4.1 Design User Interface (UI) | 4.1.1 Design Registration Page | 3 | 2023-07-10 | 2023-07-10
|  |  | 4.1.2 Design Login Page | 3 | 2023-07-10 | 2023-07-10
|  |  | 4.1.3 Design Home Page | 3 | 2023-07-11 | 2023-07-11
|  |  | 4.1.4 Design Task Creation Page | 3 | 2023-07-11 | 2023-07-11
|  |  | 4.1.5 Design Task Evaluation Page | 4 | 2023-07-12 | 2023-07-12
|  | 4.2 Design Database | 4.2.1 Identifying Entities | 3 | 2023-07-11 | 2023-07-11
|  |  | 4.2.2 Analyze Relationship between Entities | 3 | 2023-07-12 | 2023-07-12
Week 3
5 | Development | 5.1 Backend Development | 5.1.1 Integrate API with the Web-App | 8 | 2023-07-13 | 2023-07-13
|  |  | 5.1.2 Connect to API endpoints to fetch data | 8 | 2023-07-14 | 2023-07-14
|  |  | 5.1.3 Store fetched data into the database | 5 | 2023-07-15 | 2023-07-15
|  | 5.2 Frontend Development | 5.2.1 Implement UI Components | 8 | 2023-07-15 | 2023-07-15
|  |  | 5.2.2 Connect Backend with Frontend | 8 | 2023-07-16 | 2023-07-16
|  |  | 5.2.3 Bind Data from Repository to View Model and Update UI accordingly | 8 | 2023-07-17 | 2023-07-17
Week 4
6 | Quality Assurance | 6.1 Test Web-App Functionality | 6.1.1 Create test case | 4 | 2023-07-18 | 2023-07-18
|  |  | 6.1.2 Conduct system testing | 4 | 2023-07-18 | 2023-07-18
|  |  | 6.1.3 Conduct User Acceptance Testing (UAT) | 5 | 2023-07-19 | 2023-07-19
|  | 6.2 Identify and Fix Bug | 6.2.1 Identify Bugs | 3 | 2023-07-19 | 2023-07-19
|  |  | 6.2.2 Fix Bugs | 4 | 2023-07-20 | 2023-07-20
7 | Final Submission | 7.1 Cleaning | 7.1.1 Clean the code | 4 | 2023-07-20 | 2023-07-20
|  |  | 7.1.2 Organize the code | 4 | 2023-07-21 | 2023-07-21
|  | 7.2 Fix Documents | 7.2.1 Organize all documents | 3 | 2023-07-21 | 2023-07-21
|  |  | 7.2.2 Implement feedback | 4 | 2023-07-22 | 2023-07-22
|  | 7.3 Source Code, Executable file | 7.3.1 Push to Github Private Repository | 1 | 2023-07-22 | 2023-07-22
|  |  | 7.3.2 Prepare Github Documentation | 3 | 2023-07-22 | 2023-07-22
|  | 7.4 Presentation Preparation | 7.4.1 Prepare presentation slides | 3 | 2023-07-23 | 2023-07-23
|  |  | 7.4.2 Prepare speech | 3 | 2023-07-23 | 2023-07-23